## Tabelle1
Risk Management
Name | Description | Propability | Impact* | Factor | Mitigation | Responsible
iOS | The things we want to do are not possible or restricted by apple | 60% | 7 | 4.2 | Make familiar with the provided API by Apple that when ever comes a new idea it can be connected to the API whether it is possible or not | René Penkert
Deadline Pressure | At the end of the Semester we need to prepare for the examines. Risk is that the time is not scheduled properly | 60% | 3 | 1.8 | Invest more time in the earlier phase | Benedikt Bosshammer
Swift | The language Swift is still developing. So it could be possible that there are changes of the syntax or the way some stuff is implemented. | 40% | 4 | 1.6 | Decide for one Version with which the app will be programmed | Benedikt Bosshammer
SE Underestimation | The Effort for the Documentation/stuff we need to do for SE is underestimated. That correlated with our Project structure. Because we have xCode and Swift we often need to do more than one click to accomplish the same things other do with one click | 80% | 1 | 0.8 | -- | René Penkert
Exmatriculation | One of our team members might unroll form the course | 5% | 8 | 0.4 | -- | Benedikt Bosshammer
Team member gets sick |  | 10% | 2 | 0.2 | -- | Benedikt Bosshammer
*1 not much impact. 10 huge impact

## Tabelle2
Changes
Created Document | René Penkert | 2017-04-27
Added Risks | Benedikt Bosshammer | 2017-04-29
Increasd Deadline Rsik due to comming exams | Benedikt Bosshammer | 2017-05-07
Decreased SE Risk because we have done all the corrections from the last semester now | René Penkert | 2017-05-10
decreased Risk Probability for iOS because we are know verry familiar with the API´s and we know what we can accomplish in the Apple Universe and what not | René Penkert | 2017-05-15
Decreased Deadline Risk due to 2 written exams and that we did a lot of work in the last 2 weeks for SE | Benedikt Bosshammer | 2017-05-25
increased Swift Risk caused by Apple´s swift 4 presentation on WWDC 2017 | Benedikt Bosshammer | 2017-06-05
Decreased SE Risk because we are right on schedule for the final SE exam | René Penkert | 2017-06-16