## Tabelle1
Risk Managment
1 not much impact. 10 huge impact
Name | Description | Propability | Impact | Factor | Mitigation | Responsible
iOS | The things we want to do are not possible or restricted by apple | 80% | 7 | 5.6 |  | René Penkert
Deadline Pressure | At the end of the Semester we need to prepare for the examines. Risk is that the time is not scheduled properly | 60% | 3 | 1.8 | Invest more time in the earlier phase | René Penkert
Swift | The language Swift is still developing. So it could be possible that there are changes of the syntax or the way some stuff is implemented. | 40% | 4 | 1.6 | -- | Benedikt Bosshammer
SE Underestimation | The Effort for the Documentation/stuff we need to do for SE is underestimated. That correlated with our Project structure. Because we have xCode and Swift we often need to do more than one click to accomplish the same things other do with one click | 95% | 1 | 0.95 | -- | René Penkert
Exmatriculation | One of our team members might unroll form the course | 5% | 8 | 0.4 |  | Benedikt Bosshammer
Team member gets sick |  | 10% | 2 | 0.2 |  | Benedikt Bosshammer